Broad Agency Announcement (BAA)

LEGGED SQUAD SUPPORT SYSTEM

(LS3)

Defense Advanced Research Projects Agency

DARPA/TACTICAL TECHNOLOGY OFFICE (TTO)

3701 N. Fairfax Drive

Arlington, VA 22203-1714

DARPA BAA 08-71

DATE: 24 October 2008

TABLE OF CONTENTS

Part One: Overview Information	3

Part Two: Full Text of Announcement	5

I.	Funding Opportunity Description	5

A.	Program Overview	5

B.	Program Goals	5

C.	Program Structure	8

D.	Phase I Objectives	10

E.	Phase II Objectives	12

F.	Phase I Schedule and Deliverables	12

G.	Program Metrics	13

II.	Award Information	15

III.	Eligibility Information	16

A.	Eligible Applicants	16

B.	Cost Sharing/Matching	17

C.	Other Eligibility Criteria	17

IV.	Application and Submission Information	18

A.	Address to Request Application Package	18

B.	Content and Form of Application Submission	18

C.	Submission Dates and Times	25

D.	Intergovernmental Review	25

E.	Funding Restrictions	25

V.	Application Review Information	26

A.	Evaluation Criteria	26

B.	Review and Recommendation Process	29

VI.	Award Administration Information	29

A.	Award Notices	29

B.	Administrative and National Policy Requirements	30

C.	Reporting Requirements	33

D.	Electronic Systems	33

VII.	Agency Contacts	34

VIII.	Other Information	34

A.	Industry Day	34

B.	Intellectual Property	34

# Part One: Overview Information

- Federal Agency Name – Defense Advanced Research Projects Agency (DARPA), Tactical Technology Office

- Funding Opportunity Title – Legged Squad Support System (LS3)

- Announcement Type – Initial Announcement

- Funding Opportunity Number – Broad Agency Announcement (BAA) 08-71

- Catalog of Federal Domestic Assistance Numbers (CFDA) (N/A)

- Dates:

  - Posting Date: October 24, 2008

  - Industry Day:  November 12, 2008 in Arlington, VA (Registration details to be posted on FedBizOps the week of October 26, 2008)

  - Proposal Due (Initial Selection Round): January 6, 2009

  - BAA Closing Date:  October 23, 2009

- Description of the funding opportunity: The Legged Squad Support System (LS3) Program is an effort to develop a walking platform, preferably a quadruped, which can accompany dismounted soldiers and increase their combat capability.  LS3 is envisioned to augment squads by maneuvering with them in complex terrain where wheeled tactical vehicles cannot go, carry traditional squad equipment (in an effort to improve squad performance), carry new squad equipment (in an effort to give new combat and sustainment capabilities to the squad), and do so in a self-controlled fashion (requiring minimal human interaction and control).  LS3 is intended to carry 400lb or more of payload, allow for 24 hours of self-sustained capability including 20 miles of maneuver, with a total weight (including payload and fuel) of no more than 1250lb.

The LS3 program will conduct design trade studies to define an optimal system solution, perform risk reduction on critical technologies including subscale component testing, produce two (2) LS3 prototypes, and conduct testing of the end-to-end LS3 system in surrogate mission environments.  It is envisioned that this program will, at a minimum, develop and demonstrate technologies associated with the design of a deployable walking platform with sufficient payload capacity, range, and endurance with low noise signature while maintaining a total weight and volume footprint that matches dismount squad maneuver; implement gaits and control techniques that allow walking, trotting, and running/bounding as well as capabilities to jump obstacles, cross ditches, recover from disturbances, and other discrete mobility features; have a user interface capability that enables 1) self-guidance abilities for perceiving its immediate terrain environment, planning the placement of footfalls, and reliably traversing that terrain; and 2) simple soldier-to-LS3 interaction with minimal direct control of the platform’s speed and heading (joy-sticking and tele-operating are examples of direct control). Example interactions include soldier following, command by speech/gesturing, and simple guidance by waypoints (absolute or visual markers).  Hence, LS3 key program themes are embodied by platform, control, and user interface technology areas all integrated into a performing prototype legged system.

The Government is soliciting proposals for a two-phase program. This BAA requests a firm proposal for Phase I as well as a Phase II Rough Order of Magnitude (ROM) cost estimate and plan.  The estimates and plans for Phase II proposed will be evaluated for realism, but full Phase II proposals will be required as a deliverable in Phase I.  Funding decisions for subsequent phases will be based on the Phase II proposal delivered at the end of Phase I and the satisfaction of programmatic and technical criteria.

- Total amount of money to be awarded: The amount of resources made available to this BAA will depend on the quality of the proposals received.

- Anticipated individual awards – A single award is anticipated, but multiple awards are possible.

- Types of instruments that may be awarded -- Procurement contract or Other Transaction Agreement for Prototypes (OTA).

- No cost sharing is required for this BAA – See Section III-B

- Agency technical contact:

Dr. Robert Mandelbaum

DARPA/Tactical Technology Office

ATTN: BAA 08-71

3701 North Fairfax Drive

Arlington, VA 22203-1714

Fax: (703) 696-8401 or 2204

Electronic mail: BAA08-71@darpa.mil

- Agency contracting contact:

Mr Christopher Glista

DARPA/CMO

ATTN: BAA 08-71

3701 North Fairfax Drive

Arlington, VA 22203-1714

Electronic mail: BAA08-71@darpa.mil

# Part Two: Full Text of Announcement

## Funding Opportunity Description

The Defense Advanced Research Projects Agency often selects its research efforts through the Broad Agency Announcement (BAA) process.  The BAA will appear first on the FedBizOpps website, http://www.fedbizopps.gov/, then the agency website, http://www.darpa.mil/tto/solicitations.htm.  The following information is for those wishing to respond to the BAA.

### Program Overview

The Defense Advanced Research Projects Agency (DARPA) is seeking innovative solutions that will design, build, and test a legged vehicle capable of

- maneuvering robustly and nimbly among dismounted troops through complex terrain,

- carrying 400lb of equipment as well as sufficient fuel for 24 hours operation,

- sensing and negotiating terrain by autonomously selecting appropriate gaits, planning footfalls, and following a soldier through dynamic, cluttered environments, and

- operating quietly when required.

It is envisioned that this program will, at a minimum, deliver two prototype systems which will be able to follow a soldier 5-100m ahead among other troops and clutter, with zero burden on the operator to provide command or control signals.

### Program Goals

The LS3 program addresses one of the most critical challenges for modern dismounted warfare – the weight and equipment burdens placed on the dismounted squad. The ability of a squad to offload 400lb or bring along an additional 400lb of equipment, with no additional burden to the dismounted troops themselves, will dramatically improve the endurance, fighting capability, effectiveness, and morale of the dismounted squad.  This capability will enable the squad to bring more critical supplies such as ammunition, medical equipment, food, and water. It will provide the ability to bring heavy weapons and equipment such as mortars and rounds, ladders, and forced-entry gear.  It will endow the squad with platoon-level equipment and capabilities.

DARPA has defined the following non-tradable requirements of the LS3 system:

- The system must be able to carry a payload of at least 400lb, not including fuel.

- Total vehicle weight, including full-capacity fuel, must not exceed 1250lb.

- The system must be able to participate in typical squad mission profiles without adversely impacting the movement of the squad.  In particular, the system must be able to complete the following mission segments uninterrupted and without refueling.  Table 1 describes the LS3 Mission profile:

| Item | Description | Speed | Distance | Time | Noise | Auxiliary Power |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Moderate Hiking Trail | 3 mi/hr | 9.0 mi | 3.00 hr | 70dB | 0.75 hp |
| 2 | Idle - squatted | 0 mi/hr | 0.0 mi | 0.50 hr | 60dB | 0.75 hp |
| 3 | Easy Road Trail | 5 mi/hr | 5.0 mi | 1.00 hr | 70dB | 0.75 hp |
| 4 | Idle – squatted | 0 mi/hr | 0.0 mi | 0.50 hr | 60dB | 0.75 hp |
| 5 | Complex hiking trail | 1 mi/hr | 1.0 mi | 1.00 hr | 70dB | 0.75 hp |
| 6 | Easy Road Trail | 10 mi/hr | 0.5 mi | 0.05 hr | 70dB | 0 hp |
| 7 | Idle – squatted | 0 mi/hr | 0.0 mi | 0.50 hr | 60dB | 0.75 hp |
| 8 | Moderate Hiking Trail | 3 mi/hr | 3.0 mi | 1.00 hr | 70 dB | 0.75 hp |
| 9 | Moderate Hiking Trail | 3 mi/hr | 0.5 mi | 0.16 hr | 40 dB | 0.75 hp |
| 10 | Easy Road Trail | 10 mi/hr | 0.5 mi | 0.05 hr | 70 dB | 0 hp |
| 11 | Maneuver at objective | 1 mi/hr | 0.5 mi | 0.50 hr | 70 dB | 0.75 hp |
| 12 | Standby - squatted | 0 mi/hr | 0.0 mi | 15.74 hr | 40-60dB mixed | 0.75 hp |
|  | TOTALS |  | 20.0 mi | 24.00 hr |  |  |

Table 1: LS3 Mission Profile

- The minimum time between minor in-field servicing, repairs, and maintenance must be at least 24 hours.

- The minimum time between major, “motor-pool” maintenance must be at least 96 hours.

- The vehicle must be able to stand up fully loaded.  It should also be capable of righting itself after a slip, misstep, or fall.  Self-righting must be achievable with full payload, fully fueled, and on all navigable terrain types.

- The vehicle must require minimal oversight or direct control (e.g. joystick control) from an operator.  Direct control modes should only be used for error recovery, and should not be needed more than 3 times per 24-hour operational period, for no more than 5 minutes at a time.  It is the government’s desire that direct control be minimized.

- The vehicle must be able to follow a leader between 5m and 100m ahead, in dynamic, cluttered environments with other moving soldiers in close proximity.

- The vehicle must be able to follow a GPS breadcrumb trail with GPS waypoints spaced up to 100m apart, if GPS is available.

- The vehicle must be able to operate for arbitrarily long periods without GPS (on the order of tens of minutes, typical of forested or urban areas).

- The vehicle must be able to negotiate slopes up to 30( fully loaded (up, down, and side-slopes).

- The vehicle must be able to negotiate steps up to 12 inches high.

- The vehicle must be able to wade through 36 inches of water in a natural environment that will include creeks of this depth with at flow rates of 75 ft3/s.

- The vehicle must be capable of multi-directional maneuvering (forward, backwards, lateral in both directions)

- The acoustic signature of the vehicle must be no more than 70dB at 7m.  It should also be capable of operating in a quiet mode of no more than 40dB at 7m for up to 10 minutes in each hour of operation.

- The electromagnetic signature of the vehicle must be low enough so that it does not interfere with radio communications of the squad.

- The vehicle must be able to operate in temperatures between 0(F and 120(F.

- The vehicle must be small enough to be stowed in a HMMWV or JLTV rear bed including all associated gear. The vehicle must be able to be commanded in a simple manner to ingress/egress from platforms in which it is transported.

- A simple set of command function and diagnostic computer interfaces are required:

  - A small computer for soldier-like mission plan commands and dashboard monitoring of overall vehicle status.  This interface is envisioned to be in the class of a COTS smartphone.  For test/research logistical movement purposes (vehicle staging, loading/unloading, etc.), this interface should include joystick or gamepad capability to operate the vehicle prototype via remote control.

  - Data acquisition and monitoring laptop computer(s)

In addition, DARPA has the following expectations for the LS3 system based on DARPA quadruped development to date and point-of-departure analysis:

- The vehicle will transition smoothly among movement modes, without interruption of forward progress.

- The vehicle will adapt to its environment autonomously.

- The vehicle will operate safely around soldiers and civilians.

- The vehicle will negotiate rugged terrain, with unpredictable and large variations, undulations, pitfalls, and obstacles.  It should also be able to operate on a wide variety of terrain and weather types, including wet/muddy soils, snow, rain, occasional ice patches, sand, loose gravel, underbrush, vegetation coverings, and wind.  The LS3 system is expected to maintain user interface capability (e.g. soldier following) in these environments.  Specifics include:

  - Rain expectations: 1 inch/hr. rainfall

  - Snow expectations: 6” on the ground with concurrent wet, heavy snowfall

  - Sand expectations: ability to negotiate sands with grain diameters of the following subcategories: fine sand (1/8 mm - 1/4 mm), medium sand (1/4 mm - 1/2 mm), coarse sand (1/2 mm - 1 mm), and as would be encountered in desert environment dune conditions (some slope)

  - Mud expectations: ability to negotiate 10” depth

  - Wind expectations: operate with wind to 40mph including associated dust conditions

- Operate in mixes of these terrain/weather conditions as would be experienced with inclement weather conditions. The vehicle will not fall more than once every 3 hours.

- To the extent possible, passive survivability in the form of key component protection will be analyzed and included.

- To the extent possible, the vehicle should be able to reach a location designated by the leader, for example with a laser designator, out to 100m.

- The design will demonstrate due consideration for future producibility, manufacturability, supportability, and affordability of the platform.

Proposers will be asked to explore the design space for the non-tradable and desired attributes to develop their best concept for an objective system design considering military utility, mission management, operations and support, reliability and affordability.  Based on this objective system concept, proposers will build two prototypes, integrate closed-loop perception-based control, and participate in extensive government testing of the complete system.

### Program Structure

The Government anticipates that it will make a single LS3 award, but multiple awards are possible.  The LS3 program will be conducted in two phases:

- Phase I: Concept Design and Build

- Phase II: Integration and Test

#### Phase I

Phase I, anticipated to be between 24 to 36 months, will consist of the following major periods:

##### Preliminary Design

During this period, the performer will

- Complete the overall design, including trade studies, sizing of components, architecture structure/diagrams, and a comprehensive program plan for building the prototypes, integrating control and perception software, and testing.

- Purchase long-lead components.

- Build high-risk subsystems to validate correct performance.

- Build the perception head, including real-time data logging.

- Implement the control approach in simulation.

This period will culminate in a Preliminary Design Review.

##### Critical Design

During this period, the performer will

- Test all power-train and leg assembly subsystems and compile comprehensive test results

- Mature the control approach in simulation to verify the stability of multiple gaits and gait transitions, the robustness to disturbances such as bumps and slips, and self-righting.

- Collect perception data under Government supervision.

- Perform experiments on perception data sets using perception algorithms to verify correct terrain classification, footfall planning, ability to follow the leader, obstacle detection and avoidance, collision avoidance, and safe operations among moving humans in close proximity.

This period will culminate in a Critical Design Review, during which the performer will demonstrate:

- The drivetrain providing the required power output;

- A single leg performing walking and trotting motions on a test stand;

- A complete build plan for the walk out of two prototypes;

- A model in simulation showing gait selection, execution, and transitioning among gaits;

- A model in simulation that shows deliberative foot placement, stability against disturbances, and the ability to perform self-righting after a fall;

- A functional simulation model of the overall command & control architecture, including interfaces, protocols, commands, sensing, and data monitoring/recording that properly connects all LS3 system components and shows platform operation from command inputs as designed.

- The ability of the perception and planning module to

  - detect 80% of poor footholds at 3 mph and detect 80% of good footholds at 3 mph;

  - track a leader at 1 Hz;

  - classify terrain into different categories corresponding to different maneuver modes.  For example, classify into 3 categories corresponding to walking, trotting, and running gaits respectively;

  - plan footfalls to traverse the next 3m of terrain with the selected gait;

  - detect and avoid impending collisions with humans in close proximity.

##### System Build

During this period, the performer will

- Execute the build plan to integrate two vehicle prototypes;

- Integrate control algorithms to demonstrate the ability to walk and trot;

- Integrate the perception hardware .

This period will culminate in the walk-out of two (2) prototypes with capabilities meeting the Phase I Program Metrics as outlined in Section G.

The Phase I technical objectives, schedule, and deliverables are described in more detail in Sections I-D and I-F.

#### Phase II

During Phase II, anticipated to be between 12 and 18 months, the performer will integrate all perception and control algorithms to enable full functionality in complex natural and urban terrain.  The performer will also participate in Government-hosted performance evaluation testing, and will assist DARPA in developing a transition plan to the services.

This period will culminate with the prototypes being evaluated against the Phase II Program Metrics as outlined in Section G.

The Phase II objectives are described in more detail in Section I-E.

Proposers are required to propose a schedule for both Phases.

### Phase I Objectives

Phase I encompasses the complete preliminary design, final design, and build process.  For descriptive purposes, it will be outlined in sub-phases of Phase Ia (Design) and Phase Ib (Build).

The Phase Ia (Design) objectives are as follows:

- Conduct detailed technology trade studies in areas including:

  - Platform - leg design, drivetrain configuration, power/energy sizing, structural, packaging, thermal management, electronic/computer requirements, sensing, and diagnostic data collection.

- Control – simulation of gaits, control architecture, algorithms, processing techniques, sensing, influences on platform/sensing, and control requirements for negotiation of diverse terrain.

- User Interface – perception sensors, computation requirements, software architecture, influences on platform/control, and direct soldier interface.

- Create a Comprehensive LS3 Program Plan (CLPP) that includes

  - Systems engineering to tie technology trade studies in the three key areas above into a manageable and traceable selection of trades analyzed against non-tradable requirements and program metrics.

  - A weight breakdown structure/weight table

  - A realizable Phase I schedule

  - Considerations for reliability, manufacturability, affordability, and supportability.

  - Management of resources (funding, personnel, and teammates)

  - Risk mitigation

  - Logistics and test planning considerations

  - System infrastructure required of a prototype science and technology program (data acquisition, data analysis, research-level communications, test support, etc.)

  - The ability to incorporate service add-ons (e.g. a military radio) in preparation for future transition.

- Identification of key high-risk items and development of subsystems and critical components to prove design feasibility.  Examples:

  - Integration of single leg

  - Drivetrain components for bench-top dynamometer testing to expected load profiles

  - Complete control theory plan in simulation

  - User interface bench-top development for manual data collection and proof-of-principle operation (sensor head, processing hardware/software, direct interface).

- Maturing of selected technologies via trades and CLPP into a Preliminary Design and resulting Preliminary Design Review (PDR)

- Testing and analysis of subsystems built and presentation of results

- Mature controls approach, potentially with simulation applied in part to subsystem hardware developed

- User interface perception subsystems and architecture validated on contractor-collected data sets.

- Detailed design package and CLPP worthy of a Critical Design Review

The top level Phase Ib (Build) objectives are as follows:

- Execution of CLPP, hardware ordering, and implementation of CDR design package in a build phase for two (2) LS3 system prototypes.

- Maturing of the CLPP to include iterative quality control testing as build continues, safety plan, and test plans.

- Initial integration of controls hardware/software, user interface hardware/software with platform

- LS3 “walk-out” of completed preliminary integration

- Phase I testing of capability against Phase I Program Metrics (Section I-G) to include

  - Demonstration of basic walk and trot gaits

    - Flat ground

    - Natural incline

    - Pile of rubble including rocks and cinderblocks for 20m.

  - Ability to sense and display a user-interface perception data file and planned path plan

  - Demonstration of initial user interface capability to sense and follow a human leader

- An updated CLPP with complete Phase II final integration and test plan.

- Phase II Program Proposal

It is expected that the proposer will implement a rigorous system engineering process and system engineering tools in Phase I for defining and allocating the system requirements from the CLPP.  These systems engineering processes will extend across all phases of the program and provide a robust framework for linking and managing all aspects of the CLPP and LS3 PDR/CDR designs.

Specific Phase I deliverables are defined in detail for each 3-month program review in Section I-F, Phase I Schedule and Deliverables.

### Phase II Objectives

The decision to continue the program into Phase II will be based upon the Government’s determination that the performer has successfully completed the Phase I exit criteria, defined in Section I-G, Government evaluation of the Phase II proposal, as well as the availability of Phase II funds.

The top-level Phase II objectives are as follows:

- Full integration of user interface and control components onto the platform to allow full LS3 operational capability as designed

- Constant performer-based testing to mature performance across all proposed expected operational regimes

  - Terrains

  - Gaits

  - User interaction methods (following, waypoint direction, etc.)

- Maturing of CLPP to accommodate Phase II system engineering and management requirements

- Participation in at least two (2) DARPA hosted performance evaluation experiments against final program metrics at military facilities

- Development of a transition plan in conjunction with DARPA and service partners

- Final reporting

### Phase I Schedule and Deliverables

The Government envisions holding periodic program reviews throughout Phase I.  As required, the Government team will also support interim technical interchange meetings and/or telecons.  Reviews will include, at a minimum, a Phase I kick-off, mid-trade study review, PDR, mid-final design review, subsystem testing review, and CDR.

The following sections describe the deliverables desired at each review, with schedules to be proposed by the proposer.  The proposer is free to propose an alternate list of reviews and deliverables as appropriate for its concept for Phase I. However, those listed here are expected to be a minimum set desired by the government. In addition to those listed below, monthly technical and financial reports are required during each Phase. For risk reduction option tasks, the proposer’s proposal should include proposed deliverables for each review as appropriate for each option.

Initial Design Review

- Review Technology Trades progress and approach

- Review CLPP progress and approach

Preliminary Design Review

- Final Technology Trades Studies Results Review and Report

- PDR CLPP Review and Report, including program Risk Analysis

- Plan for Key Risk Subsystems Development Effort

  - Subsystem design, build plan, and testing approach

  - Bill of materials and identification of long-lead items

  - Safety Plan

Critical Design Review

- Subsystem Development Effort Results Review and Report

- Final Prototype Design Concept

  - Block diagram

  - Schematics

  - 3D CAD physical layout to the component level

  - Weight estimate/budgets

  - Software architecture

  - System specification

  - System integration approach

  - Software & hardware quality assurance planning

- CDR CLPP Review and Report, including program Risk Analysis

- Build Plan of Final Prototype Design Concept

  - Bill of materials

  - Identification of long lead items

  - Safety Plan

- Phase II Program Proposal

Prototype Completion and Initial Evaluation

- “Walk-Out” of two (2) initially and identically capable LS3 prototypes

- Completion Review – Build Results and CLPP Review

- Proposer-hosted Phase I Initial Evaluation

  - Both prototypes achieve Phase I Metrics (Section G) as an acceptance test

- (2) LS3 Prototypes delivered to the Government

- Phase II Integration and Test Plan

Phase I Final Report: The performer shall submit an annotated briefing detailing all of its Phase I activities.

### Program Metrics

In order for the Government to evaluate the effectiveness of proposed solutions in achieving the stated program objectives, exit criteria have been established for each program phase.  These exit criteria will serve as the basis for determining whether satisfactory progress is being made to warrant continued funding of the program.  The Government has identified these metrics with the intention of bounding the scope of the effort, while affording the maximum flexibility, creativity, and innovation in developing proposed solutions.  In addition to the requirements described in Section I-B, the Government has defined the exit criteria for Phase I and II in the following table:

| Technology | Phase I | Phase II |
| --- | --- | --- |
| Platform | Vehicle walk-out | 20 miles of maneuver as referenced in Table 1 LS3 Mission Profile in 24 hours, unrefueled, while carrying 400lb or more Maneuver includes complex natural/urban terrain and scenes in the presence of a squad of dismounted soldiers Max vehicle weight = 1250lb, including payload and fuel |
|  | Maneuver at each of the following speeds across even terrain for 400m (parking lot) 1mph (expected gait - walk) 3mph (expected gait – walk to trot) 5mph (expected gait – trot) 10mph (expected gait – run) |  |
|  | Maximum 70 dB noise signature, with 40 dB quiet mode |  |
| Controls | Maneuver at each of the following speeds across uneven terrain for 100m 1mph (expected gait - walk) 3mph (expected gait – walk to trot) 5mph (expected gait – trot) 10mph (expected gait – run) |  |
|  | Stability despite lateral disturbance (kick) |  |
| User Interface | Produce the following foot and body placements detections over a 50m x 2m natural terrain environment 95% of poor footholds at 3 mph & 95% of good footholds at 3 mph 80% of poor footholds at 5 mph & 80% of good footholds at 5 mph |  |
|  | Track as moving obstacles up to 5 squad members at 10 Hz with the intent of safe maneuver around and in coordination with them. |  |

## Award Information

A single award is anticipated, but multiple awards are possible. The amount of resources made available under this BAA will depend on the quality of the proposals received and the availability of funds.

The Government reserves the right to select for negotiation all, some, one, or none of the proposals received in response to this solicitation, and to make awards without discussions with proposers. The Government also reserves the right to conduct discussions if it is later determined to be necessary. If warranted, portions of resulting awards may be segregated into pre-priced options. Additionally, DARPA reserves the right to accept proposals in their entirety or to select only portions of proposals for award.  In the event that DARPA desires to award only portions of a proposal, negotiations may be opened with that proposer.  If the proposed effort is inherently divisible and nothing is gained from the aggregation, proposers should consider submitting it as multiple independent efforts.  The Government reserves the right to fund proposals in phases with options for continued work at the end of one or more of the phases.

Awards under this BAA will be made to proposers on the basis of the evaluation criteria listed below (see section labeled “Application Review Information”, Sec. V.), and program balance to provide best value to the Government.  Proposals identified for negotiation may result in a procurement contract or Other Transaction Agreement for Prototypes (OTA) depending upon the nature of the work proposed, the required degree of interaction between parties, and other factors.  The Government reserves the right to request any additional, necessary documentation once it makes the award instrument determination.  Such additional information may include, but is not limited to, Representations and Certifications.

As of the date of publication of this BAA, DARPA expects that program goals for this BAA cannot be met by proposers intending to perform 'fundamental research,' i.e., basic and applied research in science and engineering, the results of which ordinarily are published and shared broadly within the scientific community, as distinguished from proprietary research and from industrial development, design, production, and product utilization the results of which ordinarily are restricted for proprietary or national security reasons.  Notwithstanding this statement of expectation, DARPA is not prohibited from considering and selecting research proposals that, regardless of the category of research proposed, still meet the BAA criteria for submissions.  In all cases, the contracting officer shall have sole discretion to select award instrument type and to negotiate all instrument provisions with selectees.

## Eligibility Information

### Eligible Applicants

All responsible sources capable of satisfying the Government's needs may submit a proposal that shall be considered by DARPA. Historically Black Colleges and Universities (HBCUs), Small Businesses, Small Disadvantaged Businesses and Minority Institutions (MIs) are encouraged to submit proposals and join others in submitting proposals; however, no portion of this announcement will be set aside for these organizations’ participation due to the impracticality of reserving discrete or severable areas of this research for exclusive competition among these entities.

Federally Funded Research and Development Centers (FFRDCs) and Government entities (Government/National laboratories, military educational institutions, etc.) are subject to applicable direct competition limitations and cannot propose to this BAA in any capacity, unless they can clearly demonstrate the work is not otherwise available from the private sector AND they also provide written documentation citing the specific statutory authority (as well as, where relevant, contractual authority) establishing their eligibility to propose to government solicitations.  At the present time, DARPA does not consider 15 U.S.C. 3710a to be sufficient legal authority to show eligibility.  While 10 U.S.C. 2539b may be the appropriate statutory starting point for some entities, specific supporting regulatory guidance, together with evidence of agency approval, will still be required to fully establish eligibility.  DARPA will consider eligibility submissions on a case-by-case basis; however, the burden to prove eligibility for all team members rests solely with the Proposer.

Foreign participants and/or individuals may participate to the extent that such participants comply with any necessary Non-Disclosure Agreements, Security Regulations, Export Control Laws, and other governing statutes applicable under the circumstances.

Applicants considering classified submissions (or requiring access to classified information during the life-cycle of the program) shall ensure all industrial, personnel, and information system processing security requirements are in place and at the appropriate level (e.g., Facility Clearance (FCL), Personnel Security Clearance (PCL), certification and accreditation (C&A)) and any Foreign Ownership Control and Influence (FOCI) issues are mitigated prior to such submission or access.  Additional information on these subjects can be found at:  www.dss.mil.

#### Procurement Integrity, Standards of Conduct, Ethical Considerations, and Organizational Conflicts of Interest

Current federal employees are prohibited from participating in particular matters involving conflicting financial, employment, and representational interests (18 USC 203, 205, and 208.)  Once the proposals have been received and prior to the start of proposal evaluations, the Government will assess whether any potential conflict of interest exists in regards to the DARPA Program Manager, as well as those individuals chosen to evaluate proposals received under this BAA. The Program Manager is required to review and evaluate all proposals received under this BAA and to manage all selected efforts. The Program Manager for this BAA is a detailee to DARPA under the Intergovernmental Personnel Act (IPA) from Drexel University, and, as such, is highly likely to have a conflict of interest with respect to proposals utilizing that institution as a performer.  Proposers should carefully consider the composition of their performer team before submitting a proposal to this BAA.

All Proposers and proposed subcontractors must affirm whether they are providing scientific, engineering, and technical assistance (SETA) or similar support to any DARPA technical office(s) through an active contract or subcontract.  All affirmations must state which office(s) the Proposer supports and identify the prime contract numbers.  Affirmations shall be furnished at the time of proposal submission.  All facts relevant to the existence or potential existence of organizational conflicts of interest (FAR 9.5) must be disclosed.  The disclosure shall include a description of the action the Proposer has taken or proposes to take to avoid, neutralize, or mitigate such conflict.  In accordance with FAR 9.503 and without prior approval or a waiver from the DARPA Director, a Contractor cannot simultaneously be a SETA and Performer.  Proposals that fail to fully disclose potential conflicts of interests and/or do not have plans to mitigate this conflict will be rejected without technical evaluation and withdrawn from further consideration for award.

If a prospective Proposer believes that any conflict of interest exists or may exist (whether organizational or otherwise), the Proposer should promptly raise the issue with DARPA by sending Proposer's contact information and a summary of the potential conflict by email to the mailbox address for this BAA at BAA08-71@darpa.mil, before time and effort are expended in preparing a proposal and mitigation plan. If, in the sole opinion of the Government after full consideration of the circumstances, any conflict situation cannot be effectively mitigated, the proposal may be rejected without technical evaluation and withdrawn from further consideration for award under this BAA.

### Cost Sharing/Matching

Cost sharing is not required for this particular program; however, cost sharing will be carefully considered where there is an applicable statutory condition relating to the selected funding instrument (e.g., for any Other Transactions under the authority of 10 U.S.C. § 2371).  Cost sharing is encouraged where there is a reasonable probability of a potential commercial application related to the proposed research and development effort.

### Other Eligibility Criteria

#### Collaborative Efforts

Collaborative efforts/teaming are encouraged.

## Application and Submission Information

### Address to Request Application Package

This solicitation contains all information required to submit a proposal.  No additional forms, kits, or other materials are needed. This notice constitutes the total BAA. No additional information is available, nor will a formal Request for Proposal (RFP) or additional solicitation regarding this announcement be issued. Requests for same will be disregarded.

### Content and Form of Application Submission

#### Security and Proprietary Issues

The Government anticipates proposals submitted under this BAA will be unclassified.  However, if a proposal is submitted as “Classified National Security Information” as defined by Executive Order 12958 as amended, then the information must be marked and protected as though classified at the appropriate classification level and then submitted to DARPA for a final classification determination.

Proposers choosing to submit a classified proposal from other classified sources must first receive permission from the respective Original Classification Authority in order to use their information in replying to this BAA.  Applicable classification guide(s) should also be submitted to ensure the proposal is protected at the appropriate classification level.

Classified submissions shall be appropriately and conspicuously marked with the proposed classification level and declassification date.  Submissions requiring DARPA to make a final classification determination shall be marked as follows:

CLASSIFICATION DETERMINATION PENDING. Protect as though classified (insert the recommended classification level: (e.g., Top Secret, Secret or Confidential)

Classified submissions shall be in accordance with the following guidance:

Confidential and Secret Collateral Information:  Use classification and marking guidance provided by previously issued security classification guides, the Information Security Regulation (DoD 5200.1-R), and the National Industrial Security Program Operating Manual (DoD 5220.22-M) when marking and transmitting information previously classified by another Original Classification Authority.   Classified information at the Confidential and Secret level  may be mailed via appropriate U.S. Postal Service methods (e.g.,  (USPS) Registered Mail or USPS Express Mail).   All classified information will be enclosed in opaque inner and outer covers and double wrapped.  The inner envelope shall be sealed and plainly marked with the assigned classification and addresses of both sender and addressee. The inner envelope shall be address to:

Defense Advanced Research Projects Agency

ATTN:  Tactical Technology Office (TTO)

Reference:  BAA08-71

3701 North Fairfax Drive

Arlington, VA 22203-1714

The outer envelope shall be sealed with no identification as to the classification of its contents and addressed to:

Defense Advanced Research Projects Agency

Security & Intelligence Directorate, Attn: CDR

3701 North Fairfax Drive

Arlington, VA 22203-1714

All Top Secret materials: Top Secret information should be hand carried by an appropriately cleared and authorized courier to the DARPA CDR.   Prior to traveling, the courier shall contact the DARPA CDR at 571 218-4842 to coordinate arrival and delivery.

Special Access Program (SAP) Information:  SAP information must be transmitted via approved methods.  Prior to transmitting SAP information, contact the DARPA SAPCO at 703-526-4052 for instructions.

Sensitive Compartmented Information (SCI):  SCI must be transmitted via approved methods.  Prior to transmitting SCI, contact the DARPA Special Security Office (SSO) at 703-248-7213 for instructions.

Proprietary Data:  All proposals containing proprietary data should have the cover page and each page containing proprietary data clearly marked as containing proprietary data.  It is the Proposer’s responsibility to clearly define to the Government what is considered proprietary data.

Security classification guidance via a DD Form 254 will not be provided at this time since DARPA is soliciting ideas only.  After reviewing the incoming proposals, if a determination is made that the award instrument may result in access to classified information a DD Form 254 will be issued and attached as part of the award.

Proposers must have existing and in-place prior to execution of an award, approved capabilities (personnel and facilities) to perform research and development at the classification level they propose. It is the policy of DARPA to treat all proposals as competitive information, and to disclose their contents only for the purpose of evaluation.  Proposals will not be returned.  The original of each proposal received will be retained at DARPA and all other non-required copies destroyed.  A certification of destruction may be requested, provided the formal request is received at this office within 5 days after unsuccessful notification.

#### Proposal Information

Proposers must submit an original and at least three (3) copies requested, but no more than nine (9) of the full proposal and two (2) electronic copies of the full proposal [in PDF (preferred)] on a CD-ROM.  Each copy must be clearly labeled with BAA 08-71, proposer organization, proposal title (short title recommended), and Copy X of X.

All administrative correspondence and questions on this solicitation, including requests for information on how to submit a proposal to this BAA, should be directed to BAA08-71@darpa.mil or send facsimiles marked with “DARPA/TTO BAA 08-71” to (703) 807-4991. Frequently Asked Questions (FAQ) and other BAA related documents may be found on the BAA website: http://www.darpa.mil/tto/solicitations.htm. DARPA intends to use electronic mail and fax for correspondence regarding BAA 08-71.  Proposals may not be submitted by fax or e-mail; any so sent will be disregarded.  DARPA encourages use of the Internet for retrieving the BAA and any other related information that may subsequently be provided. Proposals not meeting the format described in the BAA may not be reviewed.

#### 3.  Proposal Format

All proposals must be in the format given below.  Nonconforming proposals may be rejected without review.  Proposals shall consist of two volumes.  All pages shall be printed on 8-1/2 by 11 inch paper with type not smaller than 12 point.  Smaller font may be used for figures, tables and charts.  The page limitation for proposals includes all figures, tables, and charts.  Volume I, Technical and Management Proposal, may include an attached bibliography of relevant technical papers or research notes (published and unpublished) which document the technical ideas and approach upon which the proposal is based.  Copies of not more than five (5) relevant papers can be included with the submission.  The bibliography and attached papers are not included in the page counts given below.  The submission of other supporting materials along with the proposals is strongly discouraged and will not be considered for review.  Excluding Sections I and IV, Volume I shall not exceed {60} number pages, which includes all figures, tables, and charts.  All proposals must be written in English.

#### 4.  Volume I, Technical and Management Proposal

Section I. Administrative (Not included in page count)

A.	Cover sheet to include:

(1)  BAA number, 08-71

(2)  Proposal title

(3)  Lead Organization Submitting proposal

(4) Type of business, selected among the following categories: “LARGE BUSINESS”, “SMALL DISADVANTAGED BUSINESS”, “OTHER SMALL BUSINESS”, “HBCU”, “MI”, “OTHER EDUCATIONAL”, OR “OTHER NONPROFIT”

(5) Contractor’s reference number (if any)

(6) Other team members (if applicable) and type of business for each

(7) Technical point of contact to include: salutation, last name, first name, street address, city, state, zip code, telephone, fax (if available), electronic mail (if available)

(8) Administrative point of contact to include: salutation, last name, first name, street address, city, state, zip code, telephone, fax (if available), electronic mail (if available), total funds requested from DARPA, and the amount of cost share (if any) and

(9) Date proposal was submitted.

- Official transmittal letter

- Table of Contents – The Table of Contents should be keyed to the page numbers of the proposal sections

- Additional indexes/references – such as List of Figures, List of Acronyms, etc. if desired.

Section II.  Executive Summary

The Executive Summary should provide a short overview of the proposer’s proposed Legged Squad Support System program, including a summary of objective system concept, technical approach; and top-level description of tasks, schedule and cost for each phase.

Section III. Detailed Proposal Information

.

- Technical proposal – Use a combination of engineering, technical analysis, and diagrams/drawings to present a concept that accomplishes LS3 program goals to achieve integrated platform, control, and user interface needs.

  - Provide justification for stated performance objectives and technical conclusions in the form of calculations, references, hardware identification/performance information, etc.

  - Identify and provide justification for proposed approaches in mechanical systems/subsystems, control systems, control algorithms, sensing systems, and autonomy algorithms.

  - Describe how technical concepts presented in this section relate to further analysis required in Phase I and outline the link between the presented technical approach and the Program/Management Plan.

- Program/Management Plan and Statement of Work (SOW) - In plain English, clearly define the technical tasks/subtasks to be performed, their durations, and dependencies among them.  For each task/subtask, provide:

- A general description of the objective (for each defined task/activity);

- A detailed description of the approach to be taken to accomplish each defined task/activity);

- Identification of the primary organization responsible for task execution (prime, sub, team member, by name, etc.);

- The exit criteria for each task/activity - a product, event or milestone that defines its completion.

- Define all deliverables (reporting, data, reports, software, etc.) to be provided to the Government in support of the proposed research tasks/activities.

Note: It is recommended that the SOW should be developed so that each Phase of the program is separately defined.  Do not include any proprietary information in the SOW.

- Description of the results, products, transferable technology, and expected technology transfer path enhancing that of Section II. B.  See also VIII. “Intellectual Property.”  For forms to be completed regarding intellectual property, see Section VIII.  There will be no page limit for the listed forms.

- Comparison with other ongoing research indicating advantages and disadvantages of the proposed effort.

- Discussion of proposer’s previous accomplishments and work in closely related research areas.

- Description of the facilities that would be used for the proposed effort.

- Detail including formal teaming agreements which are required to execute this program. A clearly defined organization chart for the program team which includes, as applicable: (1) the programmatic relationship of team member; (2) the unique capabilities of team members; (3) the task of responsibilities of team members; (4) the teaming strategy among the team members; and (5) identification of key personnel, including resumes and the amount of effort to be expended by each person during each program year.

H. Cost schedules and milestones for the proposed research, including estimates of cost for each task in each program year of the effort delineated by the primes and major subcontractors, total cost, and any company cost share.  Measurable critical milestones should occur at Preliminary Design, Critical Design and System Build. Additional interim, non-critical management milestones are also highly encouraged at regular intervals. Where the effort consists of multiple portions which could reasonably be partitioned for purposes of funding, these should be identified as options with separate cost estimates for each.  Additionally, proposals should clearly explain the technical approach(es) that will be employed to meet or exceed each program metric and provide ample justification as to why the approach(es) is/are feasible. The milestones must not include proprietary information.

Section IV.  Additional Information (not included in the page count)

A brief bibliography of relevant technical papers and research notes (published and unpublished) which document the technical ideas upon which the proposal is based.  Copies of not more than three (3) relevant papers can be included in the submission.

#### 5.  Volume II, Cost Proposal – {No Page Limit}

Cover sheet to include:

(1) BAA number, 08-71;

(2) Lead Organization Submitting proposal;

(3) Type of business, selected among the following categories: “LARGE BUSINESS”, “SMALL DISADVANTAGED BUSINESS”, “OTHER SMALL BUSINESS”, “HBCU”, “MI”, “OTHER EDUCATIONAL”, OR “OTHER NONPROFIT”;

(4) Contractor’s reference number (if any);

(5) Other team members (if applicable) and type of business for each;

(6) Proposal title;

(7) Technical point of contact to include: salutation, last name, first name, street address, city, state, zip code, telephone, fax (if available), electronic mail (if available);

(8) Administrative point of contact to include: salutation, last name, first name, street address, city, state, zip code, telephone, fax (if available), and electronic mail (if available);

(9) Award instrument requested: cost-plus-fixed-fee (CPFF), cost-contract—no fee, cost sharing contract – no fee, or other type of procurement contract (specify), or other transaction;

(10) Place(s)  and period(s) of performance;

(11) Total proposed cost separated by basic award and option(s) (if any);

(12) Name, address, and telephone number of the proposer’s cognizant Defense Contract Management Agency (DCMA) administration office (if known);

(13) Name, address, and telephone number of the proposer’s cognizant Defense Contract Audit Agency (DCAA) audit office (if known);

(14) Date proposal was prepared;

(15) DUNS number;

(16) TIN number; and

(17) Cage Code;

(18) Subcontractor Information; and

(19) Proposal validity period.

Detailed cost breakdown to include: (1) total program cost broken down by major cost items (direct labor, including labor categories; subcontracts; materials; other direct costs, overhead charges, etc.) and further broken down task and phase; (2) major program tasks by program year; (3) an itemization of major subcontracts and equipment purchases; (4) an itemization of any information technology (IT) purchase; (5) a summary of projected funding requirements by month; and (6) the source, nature, and amount of any industry cost-sharing; and (7) identification of pricing assumptions of which may require incorporation into the resulting award instrument (e.g., use of Government Furnished Property/Facilities/Information, access to Government Subject Matter Expert/s, etc.).  The prime contractor is responsible for compiling and providing all subcontractor proposals for the Procuring Contracting Officer (PCO).  Subcontractor proposals should include Interdivisional Work Transfer Agreements (ITWA) or similar arrangements.  Where the effort consists of multiple portions which could reasonably be partitioned for purposes of funding, these should be identified as options with separate cost estimates for each.  NOTE: for IT and equipment purchases, include a letter stating why the proposer cannot provide the requested resources from its own funding.

Supporting cost and pricing information in sufficient detail to substantiate the summary cost estimates in B. above.  Include a description of the method used to estimate costs and supporting documentation. Note: “cost or pricing data” as defined in FAR Subpart 15.4 shall be required if the proposer is seeking a procurement contract award of $650,000 or greater unless the proposer requests an exception from the requirement to submit cost or pricing data.  “Cost or pricing data” are not required if the proposer proposes an award instrument other than a procurement contract (e.g., a grant, cooperative agreement, or other transaction.)  All proprietary subcontractor proposal documentation, prepared at the same level of detail as that required of the prime, shall be made immediately available to the Government, upon request, under separate cover (i.e., mail, electronic/email, etc.), either by the Proposer or by the subcontractor organization.

All proposers requesting an 845 Other Transaction Agreement for Prototypes (OTA) must include a detailed list of payment milestones.  Each such payment milestone must include the following: milestone description, exit criteria, due date, milestone payment amount (to include, if cost share is proposed, contractor and government share amounts).  It is noted that, at a minimum, such payable milestones should relate directly to accomplishment of program technical go/no-go criteria as defined in the BAA and/or the proposer’s proposal.  Agreement type, fixed price or expenditure based, will be subject to negotiation by the Agreements Officer; however, it is noted that the Government prefers use of fixed price payable milestones to the maximum extent possible.  Do not include proprietary data.  If the proposer requests award of an 845 OTA as a nontraditional defense contractor, as so defined in the OSD guide entitled “Other Transactions (OT) Guide For Prototype Projects” dtd January 2001 (as amended) (http://www.dau.mil/pubs/Online_Pubs.asp), information must be included in the cost proposal to support the claim.  Additionally, if the proposer plans requests award of an 845 OTA, without the required one-third (1/3) cost share, information must be included in the cost proposal supporting that there is at least one non-traditional defense contractor participating to a significant extent in the proposed prototype project.

### Submission Dates and Times

#### Proposal Date

The proposal (original and designated number of hard and electronic copies) must be submitted to DARPA/Tactical Technology Office, 3701 North Fairfax Drive, Arlington, VA 22203-1714 (Attn.: BAA 08-71) on or before 4:00 p.m., local time, January 6, 2009 in order to be considered during the initial round of selections; however, proposals received after this deadline may be received and evaluated up to one year from date of posting on FedBizOpps.

DARPA will host and Industry Day on November 12, 2008.  A consolidated Frequently-Asked Question and Answer (FAQ) response will be posted after November 13, 2008. In order to receive a response to your question, submit your question by November 12, 2008 to BAA08-71@darpa.mil.  BAA 08-71 will remain open for a period of one year, 24 October 2008 through 23 October 2009. Proposals may be submitted at any time from issuance of this announcement through 1200 (ET), 23 October 2009; however, proposers are warned that the likelihood of funding is greatly reduced for proposals submitted after the initial closing date deadline.

DARPA will acknowledge receipt of complete submissions via email and assign control numbers that should be used in all further correspondence regarding proposals.

Failure to comply with the submission procedures may result in the submission not being evaluated.

### Intergovernmental Review

“Not Applicable.”

### Funding Restrictions

“Not Applicable.”

## Application Review Information

### Evaluation Criteria

Evaluation of proposals will be accomplished through a scientific/technical review of each proposal using the following criteria, in order of descending importance: (a) Ability to Meet Program Metrics; (b) Overall Scientific and Technical Merit; (c) Potential Contribution and Relevance to the DARPA Mission (d) Proposer’s Capabilities and/or Related Experience; (e) Plans and Capability to Accomplish Technology Transition; and (f) Cost Realism.  The first two criteria will have equal weight, while the next four will carry a lesser weighting and are listed in descending order of importance. These evaluation criteria are detailed in the following sections.

#### Ability to Meet Program Metrics

The feasibility and likelihood of the proposed approach for satisfying the program go/no-go metrics are explicitly described and clearly substantiated.  The proposal reflects a mature and quantitative understanding of the program metrics, the statistical confidence with which they may be measured, and their relationship to the concept of operations that will result from successful performance in the program.

- Extent to which the proposer’s LS3 system concept meets the program objectives, system requirements and performance goals based on the Program metrics criteria as listed in Section I.G. on page 14. Evaluations will primarily focus on the Phase I metrics. Phase II metrics should show sufficient detail to show integrated system capability.

- Extent to which proposer’s LS3 system conceptual design meeting the Program metrics is substantiated via analysis or previous experimental work

- Extent to which the proposer’s LS3 concept and its system capabilities has military utility.

- Extent to which the LS3 concept is innovative, feasible, and achievable within the proposer’s proposed program schedule and ROM costs.

#### Overall Scientific and Technical Merit

The proposed technical approach is innovative, feasible, achievable, complete and supported by a proposed technical team that has the expertise and experience to accomplish the proposed tasks.  Task descriptions and associated technical elements provided are complete and in a logical sequence with all proposed deliverables clearly defined such that a final product that achieves the goal can be expected as a result of award.  The proposal identifies major technical risks and planned mitigation efforts are clearly defined and feasible. These criteria will be applied to the key technology areas of platform, control, user interface, and system integration.

- Extent to which the proposed design trade studies will fully explore the available design trade space

- Extent to which the proposed technology trade studies assess the full range of technical solutions

- Extent to which the proposed design tools and trade study process will yield a robust system design.

- Extent to which the proposer has a robust system engineering process for achieving Walkout in Phase I

- Extent to which proposed plan will conduct detailed technology trade studies in areas including:

  - Platform - leg design, drivetrain configuration, power/energy sizing, structural, packaging, thermal management, electronic/computer requirements, sensing, and diagnostic data collection.

- Control – simulation of gaits, control architecture, algorithms, processing techniques, sensing, influences on platform/sensing, and control requirements for negotiation of diverse terrain.

- User Interface – perception sensors, computation requirements, software architecture, influences on platform/control, and direct soldier interface.

- Extent to which proposed Comprehensive LS3 Program Plan (CLPP) includes:

  - Systems engineering to tie technology trade studies in the three key areas above into a manageable and traceable selection of trades analyzed against non-tradable requirements and program metrics.

  - A weight breakdown structure/weight table

  - A realizable Phase I schedule

  - Considerations for reliability, manufacturability, affordability, and supportability.

  - Management of resources (funding, personnel, and teammates)

  - Risk mitigation

  - Logistics and test planning considerations

  - System infrastructure required of a prototype science and technology program (data acquisition, data analysis, research-level communications, test support, etc.)

  - The ability to incorporate service add-ons (e.g. a military radio) in preparation for future transition.

  - Identification of key high-risk items and development of subsystems and critical components to prove design feasibility.

#### Potential Contribution and Relevance to the DARPA Mission

The potential contributions of the proposed effort with relevance to the national technology base will be evaluated.  Specifically, DARPA’s mission is to maintain the technological superiority of the U.S. military and prevent technological surprise from harming our national security by sponsoring revolutionary, high-payoff research that bridges the gap between fundamental discoveries and their military use.

#### Proposer’s Capabilities and/or Related Experience

The proposer's prior experience in similar efforts must clearly demonstrate an ability to deliver products that meet the proposed technical performance within the proposed budget and schedule.  The proposed team has the expertise to manage the cost and schedule.  Similar efforts completed/ongoing by the proposer in this area are fully described including identification of other Government sponsors. Special attention will be made to experience in the areas of platform, controls and user interface.

- Professional capabilities and relevant experience of key personnel, including Program Manager, Chief Engineer, Controls Lead, Risk Management Lead and other proposed technology area leads

- Extent to which hours proposed for key personnel are consistent with described program roles

- Extent to which proposed team has previous experience in design and fabrication of a ground system

- Extent to which the proposed team has the ability to accomplish all phases of the Legged Support System program

- Extent to which proposed management construct provides adequate opportunities for addressing technical, schedule and cost issues with the Government team

#### Plans and Capability to Accomplish Technology Transition

The capability to transition the technology to the research, industrial, and operational military communities in such a way as to enhance U.S. defense, and the extent to which intellectual property rights limitations creates a barrier to technology transition.

#### Cost Realism

The objective of this criterion is to establish that the proposed costs are realistic for the technical and management approach offered, as well as to determine the proposer’s practical understanding of the effort.  This will be principally measured by cost per labor-hour and number of labor-hours proposed.  The evaluation criterion recognize that undue emphasis on cost may motivate proposers to offer low-risk ideas with minimum uncertainty and to staff the effort with junior personnel in order to be in a more competitive posture.  DARPA discourages such cost strategies.  Cost reduction approaches that will be received favorably include innovative management concepts that maximize direct funding for technology and limit diversion of funds into overhead.

After selection and before award the contracting officer will negotiate cost/price reasonableness.

Award(s) will be made to proposers whose proposals are determined to be the most advantageous to the Government, all factors considered, including the potential contributions of the proposed work to the overall research program and the availability of funding for the effort. Award(s) may be made to any proposer(s) whose proposal(s) is determined selectable regardless of its overall rating.

NOTE: PROPOSERS ARE CAUTIONED THAT EVALUATIONS RATINGS MAY BE LOWERED AND/OR PROPOSALS REJECTED IF SUBMITTAL INSTRUCTIONS ARE NOT FOLLOWED.

### Review and Recommendation Process

It is the policy of DARPA to ensure impartial, equitable, comprehensive proposal evaluations and to select the source (or sources) whose offer meets the Government's technical, policy, and programmatic goals. Pursuant to FAR 35.016, the primary basis for selecting proposals for acceptance shall be technical, importance to agency programs, and fund availability. In order to provide the desired evaluation, qualified Government personnel will conduct reviews and (if necessary) convene panels of experts in the appropriate areas.

Proposals will not be evaluated against each other since they are not submitted in accordance with a common work statement. DARPA's intent is to review proposals as soon as possible after they arrive; however, proposals may be reviewed periodically for administrative reasons. For evaluation purposes, a proposal is the document described in “Proposal Information”, Section IV.B.  Other supporting or background materials submitted with the proposal will be considered for the reviewer's convenience only and not considered as part of the proposal.

Restrictive notices notwithstanding, proposals may be handled for administrative purposes by support contractors. These support contractors are prohibited from competition in DARPA technical research and are bound by appropriate non-disclosure requirements.

Subject to the restrictions set forth in FAR 37.203(d), input on technical aspects of the proposals may be solicited by DARPA from non-Government consultants /experts who are strictly bound by the appropriate non-disclosure requirements.

It is the policy of DARPA to treat all proposals as competitive information and to disclose their contents only for the purpose of evaluation.  No proposals will be returned. Upon completion of the source selection process, the original of each proposal received will be retained at DARPA and all other copies will be destroyed.

## Award Administration Information

### Award Notices

As soon as the evaluation and award process is complete, the proposer will be notified that 1) the proposal has been selected for funding pending contract negotiations, or 2) the proposal has not been selected.  These official notifications will be sent via mail to the Technical POC identified on the proposal coversheet.

### Administrative and National Policy Requirements

#### Meeting and Travel Requirements

There will be a program kickoff meeting and all key participants are required to attend. Performers should also anticipate periodic site visits at the Program Manager’s discretion.

#### Human Use

All research involving human subjects, to include use of human biological specimens and human data, selected for funding must comply with the federal regulations for human subject protection.  Further, research involving human subjects that is conducted or supported by the DoD must comply with 32 CFR 219, Protection of Human Subjects (http://www.dtic.mil/biosys/downloads/32cfr219.pdf), and DoD Directive 3216.02, Protection of Human Subjects and Adherence to Ethical Standards in DoD-Supported Research (http://www.dtic.mil/whs/directives/corres/html2/d32162x.htm).

Institutions awarded funding for research involving human subjects must provide documentation of a current Assurance of Compliance with Federal regulations for human subject protection, for example a Department of Health and Human Services, Office of Human Research Protection Federal Wide Assurance (http://www.hhs.gov/ohrp).  All institutions engaged in human subject research, to include subcontractors, must also have a valid Assurance.  In addition, personnel involved in human subjects research must provide documentation of completing appropriate training for the protection of human subjects.

For all proposed research that will involve human subjects in the first year or phase of the project, the institution must provide evidence of or a plan for review by an Institutional Review Board (IRB) upon final proposal submission to DARPA.  The IRB conducting the review must be the IRB identified on the institution’s Assurance.  The protocol, separate from the proposal, must include a detailed description of the research plan, study population, risks and benefits of study participation, recruitment and consent process, data collection, and data analysis.  Consult the designated IRB for guidance on writing the protocol.  The informed consent document must comply with federal regulations (32 CFR 219.116).  A valid Assurance along with evidence of appropriate training all investigators should all accompany the protocol for review by the IRB.

In addition to a local IRB approval, a headquarters-level human subjects regulatory review and approval is required for all research conducted or supported by the DoD.  The Army, Navy, or Air Force office responsible for managing the award can provide guidance and information about their component’s headquarters-level review process. Note that confirmation of a current Assurance and appropriate human subjects protection training is required before headquarters-level approval can be issued.

The amount of time required to complete the IRB review/approval process may vary depending on the complexity of the research and/or the level of risk to study participants.  Ample time should be allotted to complete the approval process.  The IRB approval process can last between one to three months, followed by a DoD review that could last between three to six months.  No DoD/DARPA funding can be used towards human subjects research until ALL approvals are granted.

#### Animal Use

Any Recipient performing research, experimentation, or testing involving the use of animals shall comply with the rules on animal acquisition, transport, care, handling, and use in: (i) 9 CFR parts 1-4, Department of Agriculture rules that implement the Laboratory Animal Welfare Act of 1966, as amended, (7 U.S.C. 2131-2159); (ii) the guidelines described in National Institutes of Health Publication No. 86-23, "Guide for the Care and Use of Laboratory Animals"; (iii) DoD Directive 3216.01, “Use of Laboratory Animals in DoD Program.”

For submissions containing animal use, proposals should briefly describe plans for Institutional Animal Care and Use Committee (IACUC) review and approval. Animal studies in the program will be expected to comply with the PHS Policy on Humane Care and Use of Laboratory Animals, available at http://grants.nih.gov/grants/olaw/olaw.htm.

All Recipients must receive approval by a DoD certified veterinarian, in addition to an IACUC approval.  No animal studies may be conducted using DoD/DARPA funding until the USAMRMC Animal Care and Use Review Office (ACURO) or other appropriate DoD veterinary office(s) grant approval.  As a part of this secondary review process, the Recipient will be required to complete and submit an ACURO Animal Use Appendix, which may be found at https://mrmc.amedd.army.mil/AnimalAppendix.asp

#### Publication Approval

It is the policy of the Department of Defense for products of fundamental research to remain unrestricted to the maximum extent possible.  Contracted fundamental research:

Includes research performed under grants and contracts that are (a) Basic Research), whether performed by universities or industry or (b) applied research and performed on-campus at a university.  The research shall not be considered fundamental in those rare and exception circumstances where the applied research effort presents a high likelihood of disclosing performance characteristics of military systems or manufacturing technologies that are unique and critical to defense, and where agreement on restrictions have been recorded in the contract or grant.

It is anticipated that the performance of research resulting from the BAA will not be fundamental research.

The following provision will be incorporated into any resultant non-fundamental research procurement contract or other transaction:

There shall be no dissemination or publication, except within and between the Contractor and any subcontractors, of information developed under this contract or contained in the reports to be furnished pursuant to this contract without prior written approval of the DARPA Technical Information Officer (DARPA/TIO).  All technical reports will be given proper review by appropriate authority to determine which Distribution Statement is to be applied prior to the initial distribution of these reports by the Contractor.  Papers resulting from unclassified contracted fundamental research are exempt from prepublication controls and this review requirement, pursuant to DoD Instruction 5230.27 dated October 6, 1987.

When submitting material for written approval for open publication, the Contractor/Awardee must submit a request for public release to the DARPA TIO and include the following information: 1) Document Information:  document title, document author, short plain-language description of technology discussed in the material (approx. 30 words), number of pages (or minutes of video) and document type (briefing, report, abstract, article, or paper); 2) Event Information:  event type (conference, principle investigator meeting, article or paper), event date, desired date for DARPA's approval; 3) DARPA Sponsor:  DARPA Program Manager, DARPA office, and contract number; and 4) Contractor/Awardee's Information: POC name, e-mail and phone.  Allow four weeks for processing; due dates under four weeks require a justification.  Unusual electronic file formats may require additional processing time.  Requests can be sent either via e-mail to tio@darpa.mil or via 3701 North Fairfax Drive, Arlington VA 22203-1714, telephone (571) 218-4235.   Refer to www.darpa.mil/tio for information about DARPA's public release process.

#### Export Control

Should this project develop beyond fundamental research (basic and applied research ordinarily published and shared broadly within the scientific community) with military or dual-use applications the following apply:

(1) The Contractor shall comply with all U. S. export control laws and regulations, including the International Traffic in Arms Regulations (ITAR), 22 CFR Parts 120 through 130, and the Export Administration Regulations (EAR), 15 CFR Parts 730 through 799, in the performance of this contract.  In the absence of available license exemptions/exceptions, the Contractor shall be responsible for obtaining the appropriate licenses or other approvals, if required, for exports of (including deemed exports) hardware, technical data, and software, or for the provision of technical assistance.

(2) The Contractor shall be responsible for obtaining export licenses, if required, before utilizing foreign persons in the performance of this contract, including instances where the work is to be performed on-site at any Government installation (whether in or outside the United States), where the foreign person will have access to export-controlled technologies, including technical data or software.

(3) The Contractor shall be responsible for all regulatory record keeping requirements associated with the use of licenses and license exemptions/exceptions.

(4) The Contractor shall be responsible for ensuring that the provisions of this clause apply to its subcontractors.

#### Subcontracting

Pursuant to Section 8(d) of the Small Business Act (15 U.S.C. 637(d)), it is the policy of the Government to enable small business and small disadvantaged business concerns to be considered fairly as subcontractors to contractors performing work or rendering services as prime contractors or subcontractors under Government contracts, and to assure that prime contractors and subcontractors carry out this policy.  Each proposer who submits a contract proposal and includes subcontractors is required to submit a subcontracting plan in accordance with FAR 19.702(a) (1) and (2) should do so with their proposal.  The plan format is outlined in FAR 19.704.

### Reporting Requirements

The number and types of reports will be specified in the award document, but will include as a minimum monthly financial status reports.  The reports shall be prepared and submitted in accordance with the procedures contained in the award document and mutually agreed on before award.  Reports and briefing material will also be required as appropriate to document progress in accomplishing program metrics.  A Final Report that summarizes the project and tasks will be required at the conclusion of the performance period for the award, notwithstanding the fact that the research may be continued under a follow-on vehicle.

### Electronic Systems

#### Central Contractor Registration (CCR)

Selected proposers not already registered in the Central Contractor Registry (CCR) will be required to register in CCR prior to any award under this BAA. Information on CCR registration is available at http://www.ccr.gov.

#### Representations and Certifications

In accordance with FAR 4.1201, prospective proposers shall complete electronic annual representations and certifications at http://orca.bpn.gov.

#### Wide Area Work Flow (WAWF)

Unless using another approved electronic invoicing system, performers will be required to submit invoices for payment directly via the Internet/WAWF at http://wawf.eb.mil.  Registration to WAWF will be required prior to any award under this BAA.

#### i-Edison

The award document for each proposal selected and funding will contain a mandatory requirement for patent reports and notifications to be submitted electronically through i-Edison (http://s-edison.info.nih.gov/iEdison).

## Agency Contacts

Administrative, technical or contractual questions should be sent via e-mail to BAA08-71@darpa.mil. If e-mail is not available, fax questions to 703-807-4991, Attention:  BAA 08-71. All requests must include the name, email address, and phone number of a point of contact.

The technical POC for this effort is

Dr. Robert Mandelbaum,

DARPA/Tactical Technology Office

ATTN: BAA 08-71

3701 North Fairfax Drive

Arlington, VA 22203-1714

Electronic mail: BAA08-71@darpa.mil

The contracting POC for this effort is

Mr Christopher Glista

DARPA/CMO

ATTN: BAA 08-71

3701 North Fairfax Drive

Arlington, VA 22203-1714

Electronic mail: BAA08-71@darpa.mil

## Other Information

### Industry Day

#### An Industry Day will be held November 12, 2008. Details can be found at: http://www.darpa.mil/tto/solicitations.htm

### Intellectual Property

    - Procurement Contract Proposers

      - Noncommercial Items (Technical Data and Computer Software)

Proposers responding to this BAA requesting a procurement contract to be issued under the FAR/DFARS shall identify all noncommercial technical data and noncommercial computer software that it plans to generate, develop, and/or deliver under any proposed award instrument in which the Government will acquire less than unlimited rights, and to assert specific restrictions on those deliverables.  Proposers shall follow the format under DFARS 252.227-7017 for this stated purpose.  In the event that proposers do not submit the list, the Government will assume that it automatically has “unlimited rights” to all noncommercial technical data and noncommercial computer software generated, developed, and/or delivered under any award instrument, unless it is substantiated that development of the noncommercial technical data and noncommercial computer software occurred with mixed funding.  If mixed funding is anticipated in the development of noncommercial technical data and noncommercial computer software generated, developed, and/or delivered under any award instrument, then proposers should identify the data and software in question, as subject to Government Purpose Rights (GPR).  In accordance with DFARS 252.227-7013 Rights in Technical Data - Noncommercial Items, and DFARS 252.227-7014 Rights in Noncommercial Computer Software and Noncommercial Computer Software Documentation, the Government will automatically assume that any such GPR restriction is limited to a period of five (5) years in accordance with the applicable DFARS clauses, at which time the Government will acquire “unlimited rights” unless the parties agree otherwise.  Proposers are admonished that the Government will use the list during the evaluation process to evaluate the impact of any identified restrictions and may request additional information from the proposer, as may be necessary, to evaluate the proposer’s assertions.  If no restrictions are intended, then the proposer should state “NONE.”

A sample list for complying with this request is as follows:

| NONCOMMERCIAL |
| --- |
| Technical Data Computer Software To be Furnished With Restrictions | Basis for Assertion | Asserted Rights Category | Name of Person Asserting Restrictions |
| (LIST) | (LIST) | (LIST) | (LIST) |

      - Commercial Items (Technical Data and Computer Software)

Proposers responding to this BAA requesting a procurement contract to be issued under the FAR/DFARS shall identify all commercial technical data and commercial computer software that may be embedded in any noncommercial deliverables contemplated under the research effort, along with any applicable restrictions on the Government’s use of such commercial technical data and/or commercial computer software.  In the event that proposers do not submit the list, the Government will assume that there are no restrictions on the Government’s use of such commercial items.  The Government may use the list during the evaluation process to evaluate the impact of any identified restrictions and may request additional information from the proposer, as may be necessary, to evaluate the proposer’s assertions.  If no restrictions are intended, then the proposer should state “NONE.”

A sample list for complying with this request is as follows:

| COMMERCIAL |
| --- |
| Technical Data Computer Software To be Furnished With Restrictions | Basis for Assertion | Asserted Rights Category | Name of Person Asserting Restrictions |
| (LIST) | (LIST) | (LIST) | (LIST) |

  - Non-Procurement Contract Proposers – Noncommercial and Commercial Items (Technical Data and Computer Software)

Proposers responding to this BAA requesting an Other Transaction for Prototype shall follow the applicable rules and regulations governing these various award instruments, but in all cases should appropriately identify any potential restrictions on the Government’s use of any Intellectual Property contemplated under those award instruments in question.  This includes both Noncommercial Items and Commercial Items.  Although not required, proposers may use a format similar to that described in Paragraphs 1.a and 1.b above.  The Government may use the list during the evaluation process to evaluate the impact of any identified restrictions, and may request additional information from the proposer, as may be necessary, to evaluate the proposer’s assertions.  If no restrictions are intended, then the proposer should state “NONE.”

  - All Proposers – Patents

Include documentation proving your ownership of or possession of appropriate licensing rights to all patented inventions (or inventions for which a patent application has been filed) that will be utilized under your proposal for the DARPA program.  If a patent application has been filed for an invention that your proposal utilizes, but the application has not yet been made publicly available and contains proprietary information, you may provide only the patent number, inventor name(s), assignee names (if any), filing date, filing date of any related provisional application, and a summary of the patent title, together with either: 1) a representation that you own the invention, or 2) proof of possession of appropriate licensing rights in the invention.

    - All Proposers – Intellectual Property Representations

Provide a good faith representation that you either own or possess appropriate licensing rights to all other intellectual property that will be utilized under your proposal for the DARPA program.  Additionally, proposers shall provide a short summary for each item asserted with less than unlimited rights that describes the nature of the restriction and the intended use of the intellectual property in the conduct of the proposed research.

# Footnotes

- IT is defined as “any equipment, or interconnected system(s) or subsystem(s) of equipment that is used in the automatic acquisition, storage, manipulation, management, movement, control, display, switching, interchange, transmission, or reception of data or information by the agency.  (a)  For purposes of this definition, equipment is used by an agency if the equipment is used by the agency directly or is used by a contractor under a contract with the agency which – (1) Requires the use of such equipment; or (2) Requires the use, to a significant extent, or such equipment in the performance of a service or the furnishing of a product.  (b)  The term “information technology” includes computers, ancillary, software, firmware and similar procedures, services (including support services), and related resources.  (c)  The term “information technology” does not include – (1) Any equipment that is acquired by a contractor incidental to a contract; or (2) Any equipment that contains imbedded information technology that is used as an integral part of the product, but the principal function of which is not the acquisition, storage, manipulation, management, movement, control, display, switching, interchange, transmission, or reception of data or information.  For example, HVAC (heating, ventilation, and air conditioning) equipment such as thermostats or temperature control devices, and medical equipment where information technology is integral to its operation, are not information technology.”